## REGISTRATION
OPEN CART
IDENTIFIED BY: THEJA RAJESH REPORTED TO:RUGMA DATE:09/09/2023 VERSION NUMBER:
Test id | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
TC_RF_001 | Validate registering of an account by providing only the mandatory fields | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter new account details in the mandatory fields (First name, Last name, Email, Telephone, Password, Confirm Password and privacy policy fields. 4. Click on 'Continue' button (ER-1) 5. Click on 'Continue' button that is displayed in 'Account Success' page (ER-2) | Not Applicable | 1. User should be logged in taken to the account success page and proper details should be displayed on the page 2. User should be taken to account page and a confirm account email sent to the registered account | User is able to login to the account and proper details are displayed | pass
TC_RF_002 | Validate 'Thank you for registering' email sent to the registered email address as confirmation for registering the account | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter new account details in the mandatory fields (First name, Last name, Email, Telephone, Password, Confirm Password and privacy policy fields. 4. Click on continue button 5. Check the email address use for regestering the account. (ER-1, ER-2 ) 6. Click on the login page link from email address (ER-3) | Not Applicable | 1. Validate a confirmation email for registering the account is sent to the registered email address. 2. Validate there is 'link to the login page' provided in the email body 3. User should be taken to the login page. | A confirmation email for registering the account is sent to the registerd email address | Fail
TC_RF_003 | Validate registering an account when 'Yes' option is selected in Newsletter field | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter new account details in the mandatory fields (First name, Last name, Email, Telephone, Password, Confirm Password and privacy policy fields.) 4. Click on 'Yes' radio button for Newsletter 5. Click on continue button. (ER-1) 6. Click on continue button that is displayed on account success page. (ER-2) 7. Click on subscribe/unsubscribe for newsletter | Not Applicable | 1. User should be logged in taken to the account success page and proper details should be displayed on the page. 2. User should be taken to account page. 3. 'Yes' option should be displayed as selected by defult in the Newsletter page. | User is able to login to the account and proper details are displayed | pass
TC_RF_004 | Validate registering an account when 'No' option is selected in Newsletter field | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter new account details in the mandatory fields (First name, Last name, Email, Telephone, Password, Confirm Password and privacy policy fields.) 4. Click on 'No' radio button for Newsletter 5. Click on continue button. (ER-1) 6. Click on continue button that is displayed on account success page. (ER-2) 7. Click on subscribe/unsubscribe for newsletter | Not Applicable | 1. User should be logged in taken to the account success page and proper details should be displayed on the page. 2. User should be taken to account page. 3. 'No' option should be displayed as selected by defult in the Newsletter page. | User is logged in taken to the account success page and proper details should be displyed on page | pass
TC_RF_005 | Validate the functionality for 'First name' and 'last name' for valid inputs | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter all the mandatory fields along with the valid inputs of 'First name' and 'last name' -<Refer Test data> 4. Click on continue button. (ER-1) 5. Click on continue button that is displayed on account success page. (ER-2) | Valid inputs: a. 1 character b. 2 characters c. 30 characters d, 31 characters e. 23 characters | 1. User should be logged in taken to the account success page after entering valid inputs and proper details should be displayed on the page 2. User should be taken to account page and a confirm account email sent to the registered account | User is able to login to the account and proper details are displayed | pass
TC_RF_006 | Validate the functionality for 'First name' and 'last name' for invalid inputs | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter all the mandatory fields along with the invalid inputs of 'First name' and 'last name' -<Refer Test data> 4. Click on continue button. (ER-1) | Invalid Inputs: a. Blank b. more than 32 characters | 1. Account should not be created instead a warning message should be displayed that "First and last name must be between 1-32 characters" | Account is created and a warning message is not displyed | Fail
TC_RF_007 | Validate the resgitering an account by providing an invalid email address into E-mail field | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter all the mandatory fields along with the invalid inputs of 'E-mail address' -<Refer Test data> 4. Click on continue button. (ER-1) | Try all below invalid email address formats: 1)Thej 2) Thejas123 3) Theja@123 4)Theja123gmail.com | 1. Account should not be created instead a warning message should be displayed to provide proper E-mail address | Account is not created and a warning message is displyed | pass
TC_RF_008 | Validate the resgitering an account by providing an invalid phone number | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter all the mandatory fields along with the invalid inputs of 'phone number' -<Refer Test data> 4. Click on continue button. (ER-1) | Try all below invalid phone number formats: 1)abcd 2)123de56 | 1. Account should not be created instead a warning message should be displayed to provide proper E-mail address | Account is created and a warning message is not displyed | Fail
TC_RF_009 | Validate the resgitering an account by providing different passwords for 'Password' and 'Confirm Password' field | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter new account details in the mandatory fields (First name, Last name, Email, Telephone, Password, Confirm Password and privacy policy fields.) 4. In the 'Password' field, enter any password say '12345' 5. In the 'Confirm Password' field, enter any different password say 'abcde' 6. Click on 'continue' button. | Not Applicable | 1. Account should not be created, instead a warning message 'Password Confurm doesn't match the password' should be dislayed under password confirmation field. | Account not created and warning message is displayed | pass
TC_RF_010 | Validate all the mandatory fields are marked with red color * symbol | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Check all the fields ( First name, Last name, Email, Telephone, Password, Confirm Password and privacy policy fields). (ER-1) | Not Applicable | 1. All the specific fields mentioned in the test cases should be marked with red color * symbol | All specific fields are not marked with red colour *symbol | Fail
TC_RF_011 | Validate Registering an account by providing existing account details (e.g. E-mail address) | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter existing account details in the mandatory fields (First name, Last name, Email, Telephone, Password, Confirm Password and privacy policy fields.) 4. Click on the continue button (ER-1) | Not Applicable | 1. Account should not be created, instead a warning message should be displayed 'E-mail address already registered' | Account is not created and a warning message is displyed | pass
TC_RF_012 | Validate the resgitering an account by filling 'Password field' and not filling 'Confirm Password' field | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter new account details in the mandatory fields (First name, Last name, Email, Telephone, Password, and privacy policy fields.) 4.Don't enter into 'Confirm Password' field 5. Click on 'continue' button. (ER-1) | Not Applicable | 1. Warning message: 'Password Confirmation doesn't match password confirm field' should be displayed under password confirm field | Warning message is displyed | Pass
TC_RF_013 | Validate the resgitering an account without selecting the 'Privacy Ploicy' checkbox option | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter new account details in the mandatory fields (First name, Last name, Email, Telephone, Password, Confirm Password and Newsletter fields) 4.Don't select the 'Privacy Policy' checkbox option 5. Click on 'continue' button. (ER-1) | Not Applicable | 1. Warning meassage" You must agree to the Priacy Policy" should be displayed | Warning message is not displyed | Fail
TC_RF_014 | Validate whether the Password fields in the Register Account page are following Password Complexity Standards | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter new account details in the mandatory fields (First name, Last name, Email, Telephone, Password, Confirm Password, Privacy policy and Newsletter fields) 4. Enter simple password and not following the password complexity standards like (The passwords should be at least 8 characters in length, password should contain atleast one number, a special character, lower case and uper case letters) - <refer test data> 5. Click on the 'Continue button (ER-1) | 12345 | 1. Warning message should be displayed for following password complexity standards. | Warning message is displayed for following password complexity standards | Pass
TC_RF_015 | Validate the Password text entered to the 'Password' and 'Confirm Password' field are toggled to hide the visibilty. | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter some text to 'Password' and 'Password Confirm' field . (ER-1) | Not Applicable | 1. Password text entered into the 'Password' and 'Confirm Password' field needs to be toggled to hide its visibilty. They should be hidden by displaying *or. Symbol. | Password text enterd into password and confirm password field are not toggled into hide its visibility | Fail
TC_RF_016 | Validate the details that are entered while registering an account are stored in a database. | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Enter new account details in the mandatory fields (First name, Last name, Email, Telephone, Password, Confirm Password, Privacy policy and Newsletter fields) (ER-1) | Not Applicable | 1. All the details entered while registering an account are successfully stored in a database. | All details are stored in a database | Pass
TC_RF_017 | Validate navigating to the other pages and links provided on the 'register account' page | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' 3. Try clicking on 'Login page' link,' Privacy Policy' link, Righ column options, Menu options, Header and footer options. (ER-1) | Not Applicable | 1. User should be navigated to the respective pages without any problem. | User is navigated to respective pages without any problem | Pass
TC_RF_018 | Validate the Breadcrumb, Page Heading, Page URL, Page title of 'Register Account' Page | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' (ER-1) | Not Applicable | 1. Proper Breadcrumb, Page Heading, Page URL and Page Title should be displayed. | Breadcrumb,page heading,page url and page title are displyed | Pass
TC_RF_019 | Validate the UI of the 'Register Account' page | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' (ER-1) | Not Applicable | 1. Login page UI should adhere to the UI checklist | Login page UI are displyed | Pass
TC_RF_020 | Validate 'Register Account' functionality in all the supported environments | 1. Click on 'My Account' Drop menu 2. Click on 'Register option' (ER-1) | Not Applicable | 1. Login page functionality should work correctly in all supported envoirnments. | Login page functionality work correctly in all supported environments | Pass
RF_SU_60 | Verify captcha code should be case sensitive | 1.Open rediffsign up page 2.Verify the rediff capcha field 3.Verify the capcha field is case sensitive | HkLm | Capcha field should be case sensitive | Capcha field is case sensitive | Pass

## LOGIN
Test Case Id | Test Case title | Test Steps | Test Data | Expected Results | Actual Results | Result
TC_LF_001 | Validate the logging into the application using valid credentials | 1. Click on 'My Account' dropdown menu 2. Click on 'Login option' Validate(ER-1) 3. Enter the valid Email in 'E-mail address 'field - <Refer Test data> 4. Enter valid password in 'Password' field -<Refer Test data> 5. Click on 'Login button' Validate (ER-2) | E-mail Address: Theja123@gmail.com Password: CPnua$123 | 1. User should be navigated to the login page 2. User should be logged in and taken to the 'Account Page' | User is navigated to login page and logged in to account page | pass
TC_LF_002 | Validate logging into the application using invalid credetials (i.e. invalid email address and password) | 1. Click on 'My Account' dropdown menu 2. Click on 'Login option' 3. Enter invalid Email in 'E-mail address 'field - <Refer Test data> 4. Enter invalid password in 'Password' field -<Refer Test data> 5. Click on 'Login button' Validate (ER-1) | E-mail Address: abc124@gmail.com Password: abc124 | 1. Warning message with the text 'Warning: No match for E-mail and/or Password' should be displayed. | Warning message is displyed | pass
TC_LF_003 | Validate the logging into the application using invalid email address and valid Password | 1. Click on 'My Account' dropdown menu 2. Click on 'Login option' 3. Enter invalid Email in 'E-mail address 'field - <Refer Test data> 4. Enter valid password in 'Password' field -<Refer Test data> 5. Click on 'Login button' Validate (ER-1) | E-mail Address: abc124@gmail.com Password: CPnua$123 | 1. Warning message with the text 'Warning: No match for E-mail and/or Password' should be displayed. | Warning message is displyed | pass
TC_LF_004 | Validate the logging into the application using valid email address and invalid Password | 1. Click on 'My Account' dropdown menu 2. Click on 'Login option' 3. Enter valid Email in 'E-mail address 'field - <Refer Test data> 4. Enter invalid password in 'Password' field -<Refer Test data> 5. Click on 'Login button' Validate (ER-1) | E-mail Address: Thejs123@gmail.com Password: abc124 | 1. Warning message with the text 'Warning: No match for E-mail and/or Password' should be displayed. | warning message is displyed | pass
TC_LF_005 | Validate logging into the application without providing any credentails. | 1. Click on 'My Account' dropdown menu 2. Click on 'Login option' 3. Don't enter anything into 'E-mail address 'field 4. Don't enter anything into 'Password' field 5. Click on 'Login button' Validate (ER-1) | Not Applicable | 1. Warning message with the text 'Warning: No match for E-mail and/or Password' should be displayed. | warning message is displayed | pass
TC_LF_006 | Validate Forgot Password link is available and is working | 1. Click on 'My Account' dropdown menu 2. Click on 'Login option' Validate (ER-1) 3. Click on 'Forgot Password' link (ER-2) | Not Applicable | 1. User should be taken to login Page and 'Forgot Password' link should be displayed 2. User should be taken to 'Forgot Password' Page | Forgot password link is not working and user is not taken to forgot password page | Fail
TC_LF_007 | Validate the text in password field is toggled to hide its visibility | 1. Click on 'My Account' dropdown menu 2. Click on 'Login option' 3. Enter some text into the 'Password' field (ER-1) | Not Applicable | 1. Password text entered into the 'Password' field needs to be toggled to hide its visibility. They should be displayed with * or . Symbol | 1. Password text entered into the 'Password' field are toggled to hide its visibility. They are displayed with * or . Symbol | pass
TC_LF_008 | Validate Logging into the application after changing the password | 1. Click on 'My Account' dropdown menu 2. Click on 'Login option' 3. Enter valid Email in 'E-mail address 'field 4. Enter valid password in 'Password' field 5. Click on 'Login button' 6. Click on 'Change your Password' link 7. Enter new password in 'Password' and 'Confirm Password' field 8. Click on 'Continue' Button' 9. Click on 'My Account' dropdown menu and select "logout" 10. Repeat steps 1 to 5 (ER-1) 11. Enter new credentials given in step 7 and click on 'Login' button (ER-2) | Not Applicable | 1. User should not be logged in 2. User should be logged into the account | User is logged into the account | pass
TC_LF_009 | Validate timeout of the login session | 1. Click on 'My Account' dropdown menu 2. Click on 'Login option' (ER-1) 3. Enter valid Email in 'E-mail address 'field 4. Enter valid password in 'Password' field 5. Click on 'Login button' 6. Wait for more than 30 minutes without performing any action on the application 7. Perform any action on the application | Not Applicable | 1. User should be logged out with the proper message stating that the session got expired. | User is logged out with proper message | pass
TC_LF_010 | Validate logging in the application, closing the browser without logging out and opening the application in the browser again | 1. Click on 'My Account' dropdown menu 2. Click on 'Login option' 3. Enter valid Email in 'E-mail address 'field 4. Enter valid password in 'Password' field 5. Click on 'Login button' 6. Close the browser 7. Open the browser again and open the application URL(ER-1) | Not Applicable | 1. Logged in session should be maintained and user should not be logged out | Login session is maintained and user should be logged out | pass
TC_LF_011 | Validate logging into the application using inactive credentials | 1. Click on 'My Account' dropdown menu 2. Click on 'Login option' 3. Enter valid Email of an inactive account in 'E-mail address 'field 4. Enter valid password of an inactive account in 'Password' field 5. Click on 'Login button' (ER-!) | Not Applicable | 1. User should not be able to login | User is able to login | pass
TC_LF_012 | Validate user is able to navigate to different pages from login page | 1. Click on 'My Account' dropdown menu 2. Click on 'Login option' 3. Click on 'Continue' button under 'New Customer' section 4. Navigate back to login page and click on different options like (Right column options, header, footer, menu and other options) (ER-2) | Not Applicable | 1. User should be taken to Register Account page 2. User should be taked to appropriate pages | User is taken to register account page | pass
TC_LF_013 | Validate different ways of navigating to the login page | Validate all the below ways of navigating to Login Page: Way 1: Click the 'Login page' link from 'Register Account' page. (ER-1) 2. Click the 'Login option' from Right Column options. (ER-1) 3. Click on the 'Login option' from 'My Account' dropdown menu. (ER-1) | Not Applicable | 1. User should be navigated to the login page | User is navigated to login page | pass
TC_LF_014 | Validate the Breadcrumb, Page Heading, Page URL, Page title of 'Register Account' Page | 1. Click on 'My Account' Drop menu 2. Click on 'Login option' (ER-1) | Not Applicable | 1. Proper Breadcrumb, Page Heading, Page URL and Page Title should be displayed. | 1. Proper Breadcrumb, Page Heading, Page URL and Page Title are displayed. | pass
TC_LF_015 | Validate the UI of the 'Login Account' page | 1. Click on 'My Account' Drop menu 2. Click on 'Login option' (ER-1) | Not Applicable | 1. Login page UI should adhere to the UI checklist | 1. Login page UI adhere to the UI checklist | pass
TC_LF_016 | Validate 'Login Account' functionality in all the supported environments | 1. Click on 'My Account' Drop menu 2. Click on 'Login option' (ER-1) | Not Applicable | 1. Login page functionality should work correctly in all supported envoirnments. | 1. Login page functionality work correctly in all supported envoirnments. | pass

## RESET PASSWORD
Test Id | Test description | Test procedure | Test Data | Expected Results | Actual Results | Status
TC_FP_001 | Validate User is able to reset the password | 1. Click on 'Forgot Password' link from login page. (ER-1) 2. Enter the email address of the existing account for which you have forgot the password. 3. Click on the link for resseting the password received on the registered email. (ER-2) 4. Enter new password into 'Password' and 'Confirm Password' field. 5. Click on 'Continue' button. (ER-3) 6. Enter the Email address into the email address field and new resseted password into the password field. 7. Click on 'Login' button. (ER-4) | Not Applicable | 1. User should be taken to the 'Forgotten Password' page. 2. An Email should be sent to user with " An email with confirmation link has been sent to your email address" and user should click on the link for resseting the password. 3. Success message with text " Your Password has been updated successfully" should be displayed and user should be able to login with that password. 4. User should be taken to the 'Login' Page. | user is taken to forgot password field email is sent to the user with email confirmation link success message is displyed | pass
TC_FP_002 | Validate an email is sent with proper details on resetting the password | 1. Click on 'Forgot Password' link from login page. 2. Enter the email address of the existing account for which you have forgot the password. 3. Click on Continue button. 4. Check the registered email (ER-1), (ER-2) | Not Applicable | 1. An email should be received from the registered email address with the details of resetting the password. 2. Email should contain proper body, subject from email address and link for resetting the password. | email is received from the registerd email address and the email contain proper body subject from email address | pass
TC_FP_003 | Validate logging into the application with old password after resetting it | 1. Enter the Email in to email address field. 2. Enter the 'Old Password' into the Password field. 3. Click on 'Login' button. (ER-1) | Not Applicable | 1. User should not be able to login with the old password because the password has already been resetted. | user is able to login with the old password | pass
TC_FP_004 | Validate logging into the application with old password when you have initiated the reset password process but have not reset it | 1. Click on 'Forgot Password' link from Login page. 2. Enter the email address of the existing account for which you have forgot the password. 3. Click on 'Continue' button 4. Enter the registered Email address into the email address field and old password into the password field. 4. Click on the 'Login button' (ER-1) | Not Applicable | 1. User should be able to Login. | user is able to login | pass
TC_FP_005 | Validate resetting the password for a non-registered account | 1. Click on the 'Forgot Password' link from Login Page. 2. Enter the Email address of a non-registered account. 3. Click on the 'Continue' Button. | Not Applicable | 1. Warning message should be displayed with the test "The email address was not found in our records' | warning message is displayed | pass
TC_FP_006 | Validate how many times user can reset the password by clicking on reset link send over email | 1. Click on 'Forgot Password' link from Login page. 2. Enter the email address of the existing account for which you have forgot the password. 3. Click on 'Continue' button 4. Check the email address for which the password got reset. 5. Click on the link and reset the password. 6. Repeat steps 4 to 5 for 3 times. (ER-1) | Not Applicable | 1. User should not be able to reset the password from the link after using it for once. | user is not able to reset password from the link after using it for once | pass
TC_FP_007 | Validate user has given different passwords in password and confirm password field | 1. Click on 'Forgot Password' link from Login page. 2. Enter the email address of the existing account for which you have forgot the password. 3. Click on 'Continue' button 4. Check the email address for which the password got reset. 5. Click on the link and reset the password. 6. Enter different passwords in the 'Password' and 'Confirm Password' field. 7. Click on 'Continue' button (ER-1) | Not Applicable | 1. A field level warning with text " Password and Confirmation password does not match" should be displayed under confirm field. | 1. A field level warning with text " Password and Confirmation password does not match" are displayed under confirm field. | pass
TC_FP_008 | Validate resetting the password without giving the new password in password and confirm password field | 1. Click on 'Forgot Password' link from Login page. 2. Enter the email address of the existing account for which you have forgot the password. 3. Click on 'Continue' button 4. Check the email address for which the password got reset. 5. Click on the link and reset the password. 6. Don't enter any password into the 'Password' and 'Confirm Password' field. 7. Click on 'Continue' Button. (ER-1) | Not Applicable | 1. Field warning message should be displayed with the text: " Enter the password between 4-20 characters in the password and confirm passowrd field. | 1. Field warning message are displayed with the text: " Enter the password between 4-20 characters in the password and confirm passowrd field. | pass
TC_FP_009 | Validate Placeholders are displayed in the 'Password' and 'Confirm Password' field of your' Resest you Password' page | 1. Click on the reset password link available in the email 2. Check the 'Password' and 'Confirm' fields in the 'Reset your Password' page ( ER-1) | Not Applicable | 1. Proper placeholder texts are displayed inside the 'Password' and 'Confirm' fields of the 'Reset your Password' page | 1. Proper placeholder texts are not displayed inside the 'Password' and 'Confirm' fields of the 'Reset your Password' page | Fail
TC_FP_010 | Validate clicking 'Back' button on 'Reset your Password' page | 1. Click on the reset password link available in the email 2. Click on 'Back' button on the 'Reset your Password' page ( ER-1) | Not Applicable | 1. User should be navigated to 'Login' page | 1. User is navigated to 'Login' page | pass
TC_FP_011 | Validate 'Right Column' options are displayed on 'Reset your Password' page | 1. Click on the reset password link available in the email 2. Check for 'Right Column' options ( ER-1) | Not Applicable | 1. 'Right Columns' options should be displayed in the 'Reset your Password' page | 1. 'Right Columns' options are to be displayed in the 'Reset your Password' page | pass
TC_FP_012 | Validate resetting the password without providing a resgistered email address | 1. Click on 'Forgotten Password' link from Login page 2. Don't enter anything into the 'E-Mail Address' field 3. Click on 'Continue' button ( ER-1) | Not Applicable | 1. Field level warning message with text - E-Mail must be between 4 and 20 characters!' should be displayed for 'E-Mail Address' field | 1. Field level warning message with text - E-Mail must be between 4 and 20 characters are displayed for 'E-Mail Address' field | pass
TC_FP_013 | Validate Email address field is marked as mandatory on Forgotten Password page | 1. Click on the 'Forgotten Password' link from 'Login Page' 2. Check that Email address field on the 'Forgotten Password' page is marked manadatory (ER-1) | Not Applicable | 1. Email address should be marked mandatory | 1. Email address are not marked mandatory | Fail
TC_FP_014 | Validate entering invalid format of email into Email address field of Forgot Password page | 1. Click on the forgotten password link from login page 2. Enter an invalid Email address into the email field (ER-1) | Not Applicable | 1. Field level warning message informing the user to enter valid formatted email address should be displayed. | 1. Field level warning message informing the user to enter valid formatted email address are displayed. | Fail
TC_FP_015 | Validate back button of Forgotten Password page | 1. Click on the Forgot Password link from 'Login Page' 2. Click on the back button (ER-1) | Not Applicable | 1. User should be taken to the login page | 1. User is taken to the login page | pass
TC_FP_016 | Validate navigating to the Forgot Password page from right column option | 1. Click on the forgotten password option from the right column (ER-1) | Not Applicable | 1. User should be taken to the Forgot Password page | 1. User is taken the Forgot Password page | pass
TC_FP_017 | Validate Breadcrumb of reset your Password page | 1. Click on the Reset Password link available in the email. 2. Check the breadcrumb of the page (ER-1) | Not Applicable | 1. Proper breadcrumb should be displayed of the Reset your password page. | 1. Proper breadcrumb is displayed of the Reset your password page. | pass
TC_FP_018 | Validate the Page heading, Page URL, Page title of Reset your password page | 1. Click on the Reset Password link available in the email. 2. Check the Page heading, Page URL, and Page title of 'Reset your password' page. (ER-1) | Not Applicable | 1. Proper page heading, page url and page title should be displayed. | 1. Proper page heading, page url and page title are displayed. | pass
TC_FP_019 | Validate the Page heading, Page URL, Page title of 'Forgot Password' page | 1. Click on the 'Forgot Password' link from login page. 2. Check the Page heading, Page URL, and Page title of 'Reset your password' page. (ER-1) | Not Applicable | 1. Proper page heading, page url and page title should be displayed. | 1. Proper page heading, page url and page are displayed. | pass
TC_FP_020 | Validate the UI of 'Reset your Password' page | 1. Click on the Reset Password link available in the email. 2. Check the UI of the page (ER-1) | Not Applicable | 1. Proper Ui should adhere to the UI checklist. | 1. Proper Ui are adhere to the UI checklist. | pass
TC_FP_021 | Validate the password entered into the "New Password" and "Confirm Password" field on "Reset Password" page is toggeled to hide its visibilty | 1. Click on 'Forgot Password' link from Login page. 2. Enter the email address of the existing account for which you have forgot the password. 3. Click on 'Continue' button 4. Check the email address for which the password got reset. 5. Click on the link and reset the password. 6. Enter some text into 'Password' and 'Confirm Password' field. (ER-1) | Not Applicable | 1. Text entered into 'Password' and 'Confirm Password' field should be toggled to hide its visibility (* or . Symbol should be displayed). | 1. Text entered into 'Password' and 'Confirm Password' field are toggled to hide its visibility (* or . Symbol should be displayed). | pass
TC_FP_022 | Validate Email address entered while Login should be carry forwarded to Reset Password page | 1. Enter email address into the 'Email Address' field of 'Login Page' 2. Click on the 'Forgotten Password' link (ER-2) | Not Applicable | 1. Email address entered into the login page should be entered by default into the forgot password page | 1. Email address entered into the login page are entered by default into the forgot password page | pass
TC_FP_023 | Validate the UI of 'Forgot Password' page | 1. Click on the 'Forgotten Password' link from login page. 2. Check the UI of the page (ER-1) | Not Applicable | 1. Proper Ui should adhere to the UI checklist. | 1. Proper Ui are to the UI checklist. | pass
TC_FP_024 | Validate the breadcrumb of 'Forgot Password' page | 1. Click on the 'Forgotten Password' link from login page. 2. Check the breadcrumb of the page (ER-1) | Not Applicable | 1. Proper breadcrumb should be displayed of the forgot password page. | 1. Proper breadcrumb are displayed of the forgot password page. | pass
TC_FP_025 | Validate Password reset functionality in all supported envoirnments | 1. Click on the 'Forgot Password' link from Login Page. (ER-1) | Not Applicable | 1. Reset password functionality should work correctly in all supported envoirnments. | 1. Reset password functionality work correctly in all supported envoirnments. | pass

## CHECKOUT
Test Id | Test Description | Test Procedure | Test Data | Expected Results | Actual Result | Status
TC_CO_001 | Validate navigating to the 'Checkout' page when there are no products added to the shopping cart | 1. Click on the 'Check out' header option (ER-1) | Not Applicable | 1. User should be taken to the empty shopping cart page instead of check out page | user is taken to empty shopping cart page | pass
TC_CO_002 | Validate navigating to the 'Checkout' page from 'Shopping Cart' page | 1. Search for any existing product 2. Click on 'Add to Cart' button on the displayed product 3. Click on 'Shopping Cart' link in the displayed success message 4. Click o the 'Checkout' button in the 'Shopping Cart' page (ER-1) | Not Applicable | 1. User should be taken to the checkout page | user is taken to checkout page | pass
TC_CO_003 | Validate navigating to the 'Checkout' page using 'Shopping Cart' header option | 1. Click on 'Checkout' header option (ER-1) | Not Applicable | 1. User should be taken to the checkout page | user is taken to checkout page | pass
TC_CO_004 | Validate navigating to the 'Checkout page' using 'Checkout' option in cart block | 1. Click on the 'Cart' button which is displayed in the top of page besides search bar 2. Click on 'Checkout' option displayed in the Cart block (ER_1) | Not Applicable | 1. User should be taken to the checkout page | user is taken to checkout page | pass
TC_CO_005 | Validate Checkout as SignedIn User ( SignIn Checkout ) by using an existing address during checkout | 1. Enter any existing Product name into the Search text box field - <Refer Test Data> 2. Click on the button having search icon 3. Click on 'Add to Cart' button on the Product displayed in the Search results 4. Click on the 'shopping cart!' link in the displayed success message 5. Click on 'Checkout' button in the 'Shopping Cart' page (Validate ER-1) 6. Click on 'Continue' button ( ER-2) 7. Click on 'Continue' button ( ER-3) 8. Click on 'Continue' button ( ER-4) 9. Select the 'Terms & Conditions' checkbox field 10. Click on 'Continue' button ( ER-5) 11. Click on 'Confirm Order' button ( ER-6) | Product Name: iMac | 1. 'I want to use an existing address' radio option should be displayed as selected by default in the 'Payment Address Details' section and the correct address details should be displayed in the text field 2. 'I want to use an existing address' radio option should be displayed as selected by default in the 'Shipping Address Details' section and the correct address details should be displayed in the text field 3. 'Flat Shipping Rate - $8.00' radio option should be displayed as selected by default in the 'Delivery Method' section 4. 'Cash On Delivery' radio option should be displyaed as selected by default in the 'Payment Method' section 5. Proper details to be displayed in the 'Confirm Order' section 6. Order should be placed and User should be taken to Success page (Proper details should be displayed in the Order Success page) |  | pass
TC_CO_006 | Validate Checkout as SignedIn User ( SignIn Checkout ) by entering new address into the mandatory fields of the Payment Address Details section during checkout | 1. Enter any existing Product name into the Search text box field - <Refer Test Data> 2. Click on the button having search icon 3. Click on 'Add to Cart' button on the Product displayed in the Search results 4. Click on the 'shopping cart!' link in the displayed success message 5. Click on 'Checkout' button in the 'Shopping Cart' page ( ER-1) 6. Select 'I want to use a new address' radio option ( ER-2) 7. Enter details only into the mandatory fields - First Name, Last Name, Address1, City, Country and Region/State 8. Click on 'Continue' button ( ER-3) 9. Click on 'Continue' button ( ER-4) 8. Click on 'Continue' button ( ER-5) 9. Select the 'Terms & Conditions' checkbox field 10. Click on 'Continue' button ( ER-6) 11. Click on 'Confirm Order' button ( ER-7) | Product Name: iMac | 1. 'I want to use an existing address' radio option should be displayed as selected by default in the 'Payment Address Details' section and the correct address details should be displayed in the text field 2. New address fields - First Name, Last Name, Company, Address1, Address2, City, Post Code, Country, Country and Region/State should be displayed 3. 'I want to use an existing address' radio option should be displayed as selected by default in the 'Shipping Address Details' section and the correct address details should be displayed in the text field 4. 'Flat Shipping Rate - $8.00' radio option should be displayed as selected by default in the 'Delivery Method' section 5. 'Cash On Delivery' radio option should be displyaed as selected by default in the 'Payment Method' section 6. Proper details to be displayed in the 'Confirm Order' section 7. Order should be placed and User should be taken to Success page (Proper details should be displayed in the Order Success page) |  | pass
TC_CO_007 | Validate Checkout as SignedIn User ( SignIn Checkout ) by entering new address into all the fields of the Payment Address Details section during checkout | 1. Enter any existing Product name into the Search text box field - <Refer Test Data> 2. Click on the button having search icon 3. Click on 'Add to Cart' button on the Product displayed in the Search results 4. Click on the 'shopping cart!' link in the displayed success message 5. Click on 'Checkout' button in the 'Shopping Cart' page ( ER-1) 6. Select 'I want to use a new address' radio option ( ER-2) 7. Click on the 'Continue' Button | Product Name: iMac | 1. 'I want to use an existing address' radio option should be displayed as selected by default in the 'Payment Address Details' section and the correct address details should be displayed in the text field 2. New address fields - First Name, Last Name, Company, Address1, Address2, City, Post Code, Country, Country and Region/State should be displayed 3. 'I want to use an existing address' radio option should be displayed as selected by default in the 'Shipping Address Details' section |  | pass
TC_CO_008 | Validate text fields in Payment Address Details of the Checkout page has Placeholders | 1. Enter any existing Product name into the Search text box field - <Refer Test Data> 2. Click on the button having search icon 3. Click on 'Add to Cart' button on the Product displayed in the Search results 4. Click on the 'shopping cart!' link in the displayed success message 5. Click on 'Checkout' button in the 'Shopping Cart' page 6. Select 'I want to use a new address' radio option 7. Check all the text fields - First Name, Last Name, Company, Address1, Address 2, City and Post Code for Placeholder text (ER-1) | Product Name: iMac | 1. Proper Place Holder texts should be displayed in the text fields - First Name, Last Name, Company, Address1, Address 2, City and Post Code | proper place holder texts are displyed in the text field | pass
TC_CO_009 | Validate without entering any fields in the Billing Section of the Checkout Page | 1. Enter any existing Product name into the Search text box field - <Refer Test Data> 2. Click on the button having search icon 3. Click on 'Add to Cart' button on the Product displayed in the Search results 4. Click on the 'shopping cart!' link in the displayed success message 5. Click on 'Checkout' button in the 'Shopping Cart' page 6. Select 'I want to use a new address' radio option 7. Don't enter anything into the fields of 'Payment Address Details' Section of 'Checkout' page (Validate ER-1) | Product Name: iMac | 1. Proper field level warning messages should be displayed for all the mandatory fields in the Payment Address Details section | proper field level warning message are displyed | pass
TC_CO_010 | Validate Checkout as SignedIn User ( SignIn Checkout ) by entering new address into the mandatory fields of the Shipping Address Details section during checkout | 1. Enter any existing Product name into the Search text box field - <Refer Test Data> 2. Click on the button having search icon 3. Click on 'Add to Cart' button on the Product displayed in the Search results 4. Click on the 'shopping cart!' link in the displayed success message 5. Click on 'Checkout' button in the 'Shopping Cart' page (Validate ER-1) 6. Click on 'Continue' button (Validate ER-2) 7. Select 'I want to use a new address' radio option (Validate ER-3) 8. Enter details only into the mandatory fields - First Name, Last Name, Address1, City, Country and Region/State 9. Click on 'Continue' button (Validate ER-4) 8. Click on 'Continue' button (Validate ER-5) 9. Select the 'Terms & Conditions' checkbox field 10. Click on 'Continue' button (Validate ER-6) 11. Click on 'Confirm Order' button (Validate ER-7) | Product Name: iMac | 1. 'I want to use an existing address' radio option should be displayed as selected by default in the 'Payment Address Details' section and the correct address details should be displayed in the text field 2. 'I want to use an existing address' radio option should be displayed as selected by default in the 'Shipping Address Details' section and the correct address details should be displayed in the text field 3. New address fields - First Name, Last Name, Company, Address1, Address2, City, Post Code, Country, Country and Region/State should be displayed 4. 'Flat Shipping Rate - $8.00' radio option should be displayed as selected by default in the 'Delivery Method' section 5. 'Cash On Delivery' radio option should be displyaed as selected by default in the 'Payment Method' section 6. Proper details to be displayed in the 'Confirm Order' section 7. Order should be placed and User should be taken to Success page (Proper details should be displayed in the Order Success page) |  | pass
TC_CO_011 | Validate Checkout as SignedIn User ( SignIn Checkout ) by entering new address into all the fields of the Shipping Address Details section during checkout | 1. Enter any existing Product name into the Search text box field - <Refer Test Data> 2. Click on the button having search icon 3. Click on 'Add to Cart' button on the Product displayed in the Search results 4. Click on the 'shopping cart!' link in the displayed success message 5. Click on 'Checkout' button in the 'Shopping Cart' page (Validate ER-1) 6. Click on 'Continue' button (Validate ER-2) 7. Select 'I want to use a new address' radio option (Validate ER-3) 8. Enter details into all the fields - First Name, Last Name, Company, Address1, Address 2, City, Post Code, Country and Region/State 10. Click on 'Continue' button (Validate ER-4) 11. Click on 'Continue' button (Validate ER-5) 12. Select the 'Terms & Conditions' checkbox field 13. Click on 'Continue' button (Validate ER-6) 14. Click on 'Confirm Order' button (Validate ER-7) | Product Name: iMac | 1. 'I want to use an existing address' radio option should be displayed as selected by default in the 'Payment Address Details' section and the correct address details should be displayed in the text field 2. 'I want to use an existing address' radio option should be displayed as selected by default in the 'Shipping Address Details' section and the correct address details should be displayed in the text field 3. New address fields - First Name, Last Name, Company, Address1, Address2, City, Post Code, Country, Country and Region/State should be displayed 4. 'Flat Shipping Rate - $8.00' radio option should be displayed as selected by default in the 'Delivery Method' section 5. 'Cash On Delivery' radio option should be displyaed as selected by default in the 'Payment Method' section 6. Proper details to be displayed in the 'Confirm Order' section 7. Order should be placed and User should be taken to Success page (Proper details should be displayed in the Order Success page) |  | Fail
TC_CO_012 | Validate text fields in Shipping Address Details of the Checkout page has Placeholders | 1. Enter any existing Product name into the Search text box field - <Refer Test Data> 2. Click on the button having search icon 3. Click on 'Add to Cart' button on the Product displayed in the Search results 4. Click on the 'shopping cart!' link in the displayed success message 5. Click on 'Checkout' button in the 'Shopping Cart' page 6. Click on 'Continue' button 7. Select 'I want to use a new address' radio option in the 'Shipping Address Details' section 8. Check all the text fields - First Name, Last Name, Company, Address1, Address 2, City and Post Code for Placeholder text (Validate ER-1) | Product Name: iMac | 1. Proper Place Holder texts should be displayed in the text fields - First Name, Last Name, Company, Address1, Address 2, City and Post Code | proper place holder texts are displyed in the text field | pass
TC_CO_013 | Validate without entering any fields in the Shipping Address Details Section of the Checkout Page | 1. Enter any existing Product name into the Search text box field - <Refer Test Data> 2. Click on the button having search icon 3. Click on 'Add to Cart' button on the Product displayed in the Search results 4. Click on the 'shopping cart!' link in the displayed success message 5. Click on 'Checkout' button in the 'Shopping Cart' page 6. Click on 'Continue' button 7. Select 'I want to use a new address' radio option 8. Don't enter anything into the fields of 'Shipping Address Details' Section of 'Checkout' page (Validate ER-1) | Product Name: iMac | 1. Proper field level warning messages should be displayed for all the mandatory fields in the Shipping Address Details section | proper level warning message are not to | Fail
TC_CO_014 | Validate adding comments about your order in the 'Delivery Method' section of Checkout page | 1. Enter any existing Product name into the Search text box field - <Refer Test Data> 2. Click on the button having search icon 3. Click on 'Add to Cart' button on the Product displayed in the Search results 4. Click on the 'shopping cart!' link in the displayed success message 5. Click on 'Checkout' button in the 'Shopping Cart' page 6. Click on 'Continue' button 7. Click on 'Continue' button 8. Enter any text into the 'Add Comments About Your Order' text field 8. Click on 'Continue' button (Validate ER-1) 9. Select the 'Terms & Conditions' checkbox field 10. Click on 'Continue' button 11. Click on 'Confirm Order' button (Validate ER-2) | Product Name: iMac | 1. Comment entered should be displayed as it is in the 'Payment Method' section 2. Order should be placed and User should be taken to Success page (Proper details should be displayed in the Order Success page) | 1. Comment entered are displayed as it is in the 'Payment Method' section 2. Order is placed and User is taken to Success page (Proper details should be displayed in the Order Success page) | pass
TC_CO_015 | Validate adding comments about your order in the 'Payment Method' section of Checkout page | 1. Enter any existing Product name into the Search text box field - <Refer Test Data> 2. Click on the button having search icon 3. Click on 'Add to Cart' button on the Product displayed in the Search results 4. Click on the 'shopping cart!' link in the displayed success message 5. Click on 'Checkout' button in the 'Shopping Cart' page 6. Click on 'Continue' button 7. Click on 'Continue' button 8. Click on 'Continue' button 9. Enter any text into the 'Add Comments About Your Order' text field 10. Select the 'Terms & Conditions' checkbox field 11. Click on 'Continue' button 12. Click on 'Confirm Order' button (Validate ER-1) | Product Name: iMac | 1. Order should be placed and User should be taken to Success page (Proper details should be displayed in the Order Success page) | 1. Order is placed and User is taken to Success page (Proper details should be displayed in the Order Success page) | pass
TC_CO_016 | Validate the UI of 'Checkout' functionality | 1. Check the UI of the functionality related to 'Checkout' (Validate ER-1) | Not Applicable | 1. Proper UI adhering to the UI checklist should be displayed for the 'Checkout' functionality | 1. Proper UI adhering to the UI checklist are displayed for the 'Checkout' functionality | pass
TC_CO_017 | Validate the 'Checkout' functionality in all the supported environments | 1. Check the 'Checkout' functionality in all the supported environments (Validate ER-1) | Not Applicable | 1. 'Checkout' functionality should work correctly in all the supported environments | 1. 'Checkout' functionality work correctly in all the supported environments | pass

## ADD TO CART
Test Id | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
TC_ATC_001 | Validate adding the product to cart from product display page | 1. Enter any existing product name in the search bar 2. Click on the product displayed in the search results. 3. Click on 'Add to Cart' button (ER-1) 4. Click on the 'Shopping Cart' link displayed in the success message. (ER-2) | Not Applicable | 1. Success message with the text " You have added product name to your shopping cart" should be displayed. 2. Product should be successfully displayed in the shopping cart page. | 1. Success message with the text " You have added product name to your shopping cart" is displayed. 2. Product is displayed in the shopping cart page. | pass
TC_ATC_002 | Validate adding the product to cart from product compare page | 1. Click on 'Add to cart' button that is displayed on the 'Product Comparison' page (ER-1) 2. Click on the 'Shopping Cart' link displayed in the success message (ER-2). | Not Applicable | 1. Success message with the text " You have added product name to your shopping cart" should be displayed. 2. Product should be successfully displayed in the shopping cart page. | 1. Success message with the text " You have added product name to your shopping cart" is displayed. 2. Product is successfully displayed in the shopping cart page. | pass
TC_ATC_003 | Validate adding the product to cart from wishlist page | 1. Click on 'Add to cart' button that is displayed on the 'Wishlist' page (ER-1) 2. Click on the 'Shopping Cart' link displayed in the success message (ER-2). | Not Applicable | 1. Success message with the text " You have added product name to your shopping cart" should be displayed. 2. Product should be successfully displayed in the shopping cart page. | 1. Success message with the text " You have added product name to your shopping cart" is displayed. 2. Product is successfully displayed in the shopping cart page. | pass
TC_ATC_004 | Validate adding the product to cart displayed in the category or sub-category page | 1. Click on 'Add to Cart' button that is displayed for any product available in 'Category' or 'Sub-Category' pages. (ER-1) 2. Click on the 'Shopping Cart' link displayed in the success message. (ER-2). | Not Applicable | 1. Success message with the text " You have added product name to your shopping cart" should be displayed. 2. Product should be successfully displayed in the shopping cart page. | 1. Success message with the text " You have added product name to your shopping cart" is displayed. 2. Product isdisplayed in the shopping cart page. | pass
TC_ATC_005 | Validate adding the product to cart from product displayed in 'featured' section of homepage | 1. Click on 'Add to Cart' button that is displayed for any product available in ' Featured' section of Homepage. (ER-1) 2. Click on the 'Shopping Cart' link displayed in the success message. (ER-2). | Not Applicable | 1. Success message with the text " You have added product name to your shopping cart" should be displayed. 2. Product should be successfully displayed in the shopping cart page. | 1. Success message with the text " You have added product name to your shopping cart is displayed. 2. Product is successfully displayed in the shopping cart page. | pass
TC_ATC_006 | Validate adding the product to Cart from the Related Products section of the Product Display Page | 1. Click on 'Add to Cart' button that is displayed for any product available in ' Product Section' on the product display page. (ER-1) 2. Click on the 'Shopping Cart' link displayed in the success message. (ER-2). | Not Applicable | 1. Success message with the text " You have added product name to your shopping cart" should be displayed. 2. Product should be successfully displayed in the shopping cart page. | 1. Success message with the text " You have added product name to your shopping cart" is displayed. 2. Product is successfully displayed in the shopping cart page. | pass
TC_ATC_007 | Validate the UI of 'Add to Cart' functionality | 1. Check the UI of the functioanality related to 'Add to Cart' ( ER-1) | Not Applicable | 1. Proper UI adhering to the UI checklist should be displayed for the 'Add to Cart' functionality | 1. Proper UI adhering to the UI checklist are displayed for the 'Add to Cart' functionality | pass
TC_ATC_008 | Validate the functionality of 'Add to Cart' page is supported in all envoirnments | 1. Check the 'Add to Cart' functionality in all the supported environments (ER-1) | Not Applicable | 1. 'Add to Cart' functionality should work correctly in all the supported environments | 1. 'Add to Cart' functionality work correctly in all the supported environments | pass

## BUG REPORT
Bug ID | Bug Description | Steps to Reproduce | Severity | Priority | Screenshot | Status
OPENCART-BUG-1 | Thank you for registering 'Email' is not received to registered email address after registering an account | 1. Open the Application URL 2. Click on 'My Account' dropmenu 3. Select 'Register' option 4. Enter the new User valid details into the 'Register Account' page 5. Select the 'Privacy Policy' checkbox option 6. Click on 'Continue' button | Major | Medium |  | New
OPENCART-BUG-2 | User is able to register an account by providing invalid inputs for 'first name' and 'last name' | 1. Open the Application URL 2. Click on 'My Account' dropmenu 3. Select 'Register' option 4. Enter valid details into the fields displayed on the 'Register Account' page 5. Enter invalid inputs for'First' and 'Last' name 6. Select 'Privacy Policy' checkbox field 7. Click on 'Continue' button | Major | Medium |  | New
OPENCART-BUG-3 | User is able to register an account by providing invalid phone number | 1. Open the Application URL 2. Click on 'My Account' dropmenu 3. Select 'Register' option 4. Enter valid details into the fields displayed on the 'Register Account' page 5. Enter invalid phone number say abcde into the 'Telephone' field 6. Select 'Privacy Policy' checkbox field 7. Click on 'Continue' button | Major | Medium |  | New
OPENCART-BUG-4 | Mandatory fields are not marked with red * symbol | 1. Open the Application URL 2. Click on 'My Account' dropmenu 3. Select 'Register' option 4. Check the mandatory fields are maked with red color *symbol | Major | Medium |  | New
OPENCART-BUG-5 | Privacy policy' checkbox is not selected while registering the account | 1. Open the Application URL 2. Click on 'My Account' dropmenu 3. Select 'Register' option 4. Check either privacy policy checkbox is selected or not | Minor | Low |  | New
OPENCART-BUG-6 | Password' and 'Password Confirm' field are accepting simple password for registering an account | 1. Open the Application URL in any browser 2. Click on 'My Account' dropmenu 3. Select 'Register' option 4. Enter details into all the mandatory fields 5. Enter simple password say 'abcd' into the 'Password' and 'Password Confirm' fields 6. Select 'Privacy Policy' checkbox field 7. Click on 'Continue' button | Major | Medium |  | New
OPENCART-BUG-7 | Forgot Password link is not working | 1. Click on 'My Account' dropdown menu 2. Click on 'Login option' 3. Click on 'Forgot Password' link 4. Click on'Continue' button | Minor | Low |  | New
OPENCART-BUG-8 | User is not getting automatically logged out after 30 minutes of inactivity | 1. Login to the Application with valid credentials 2. Don't perform any action for next 30 minutes 3. Try to perform any action after the above 30 minutes like Search a product etc. | Minor | Low |  | New
OPENCART-BUG-9 | After logging out and browisng back, user is not getting logged out | 1. Login to the Application with valid credentials 2. Logout of the account and browse back 3. Login again | Major | Medium |  | New
OPENCART-BUG-10 | User is not getting logged in after logging out and then immediately logging in | 1. Login to the Application with valid credentials 2. Logout of the account and browse back 3. Login again | Major | Medium |  | New
OPENCART-BUG-11 | Placeholders are not getting displayed in 'Password' and 'Confirm Password' field | 1. Login to the Application with valid credentials 2. Check the placeholders are being displayed in 'Password' and 'Confirm Password' field | Minor | Low |  | New
OPENCART-BUG-12 | Email Address' on 'Forgot Password' page is not marked as mandatory | 1. Click on 'Forgot Password' link from login page 2. Check that email address field is marked as mandatory or not | Mjaor | Medium |  | New
OPENCART-BUG-13 | Email Address from login page is not getting carry forwarded to 'Forgot Password' page | 1. Open Application URL 2. Click on 'My Account' dropmenu 3. Select 'Login' option 4. Enter email address into the 'E-Mail Address' text field 5. Click on 'Forgotten Password' link | Minor | Medium |  | New
OPENCART-BUG-14 | User is not being taken to the empty shopping cart page | 1. Open the Application URL and ensure that there is no product added to the shopping cart 2. Click on the 'Check out' header option | Minor | Medium |  | New
OPENCART-BUG-15 | New address radio button is not being displayed | 1. Enter any existing Product name by clicking on the button having search button 2. Click on 'Add to Cart' button 3. Click on the 'shopping cart!' link in the displayed success message and click on the checkout button 4. Select 'I want to use a new address' radio option 5. Click on the Continue button | Minor | Low |  | New
OPENCART-BUG-16 | Warning message didn't display for filling all the mandatory fields in shipping address details section | 1. Enter any existing Product name by clicking on the button having search button 2. Click on 'Add to Cart' button 3. Click on the 'shopping cart!' link in the displayed success message and click on the checkout button 4. Select 'I want to use a new address' radio option 5. Click on the Continue button 6. Don't enter anything into the fields of 'Shipping Address Details' Section of 'Checkout' page | Minor | Medium |  | New

## Sheet1
OPEN CART
MODULE NAME | DEFECT DISTRIBUTION
REGISTRATION | 4
LOGIN | 1
RESET PASSWORD | 3
CHECKOUT | 3
ADD TO CART | 0